## Errata
Bug ID | Test ID | Failure Summary | Expected | Actual | Root Cause | Suggested Fix | Severity | Status | Owner
BUG-007 | RST-002..005 | Hardware Reset Pin (RES) Not Implemented | RES input pin must clear all registers and internal state on assertion | Usart2 has no sc_in<bool> rst port and no SWRST register. Offset 0x14 falls into default: no-op case in b_transport. CON/STATUS/rbuf_full survive what should be a reset. m_frame_done_ev is not cancelled. | RES pin not modelled in Usart2 sc_module | Option A: add sc_in<bool> rst port; drive from sc_main. Option B: add OFF_SWRST=0x14 case — on write 1: m_con=0, m_status=0, m_rbuf=0, m_rbuf_full=false, m_frame_done_ev.cancel(), sync_irq_trace() | High | Open | VP Team
BUG-001 | RW-002 | CON Reserved Bits [31:16] Stored | CON[31:16] must read 0 (reserved per spec) | VP model stores full 32-bit m_con including reserved bits | Model stores raw register write without masking | Mask reserved bits: m_con = value & 0x0000FFFFu in b_transport | Low | Open | VP Team
BUG-002 | RW-006 | BG Register Not Implemented | BG at offset 0x0C: 13-bit reload register + live downcounter | VP model b_transport default case — BG is a no-op; reads return 0 | Registers beyond STATUS (0x20) not implemented in Usart2::b_transport | Add OFF_BG case; implement m_bg_reload and simulated downcounter | Medium | Open | VP Team
BUG-003 | RW-007 | FDR Register Not Implemented | FDR at offset 0x10: STEP[7:0]+DM[8]; active when CON.FDE=1 | VP model b_transport default case — FDR is a no-op | Registers beyond STATUS (0x20) not implemented | Add OFF_FDR case; implement sigma-delta accumulator logic | Medium | Open | VP Team
BUG-004 | LB-004 | CON.LB Loopback Not Functional | CON.LB=1 must internally connect TSR output to RSR input | CON.LB is stored but sc_fifo routing is hard-wired in sc_main; loopback has no effect | sc_fifo connections are fixed at elaboration time in sc_main | In tx_deliver_method: if (m_con & CON_LB) write to own rx_port else tx_port | Medium | Open | VP Team
BUG-005 | ADV-006 | RBUF Stale Value After rbuf_full Clear | Spec: RBUF holds valid data until rbuf_full asserted; behaviour after clear is impl-defined | VP model m_rbuf retains last byte; second read after drain returns stale value | m_rbuf is not cleared on RBUF read; only m_rbuf_full is cleared | Document VP behaviour explicitly; add note in usart2.h | Info | Documented | VP Team
BUG-006 | FN-003/ADV-001 | EIR Gating Depends on CON_OEN | EIR must fire simultaneously with RIR only when CON.OEN=1 | VP model checks (m_con & CON_OEN) in rx_thread — correct behaviour | N/A — model implements this correctly | No fix required — compliant | None | Closed | N/A